UNIVERSITY SERVICES
MANAGEMENT SYSTEM

PROJECT PLANNING & MANAGEMENT

Version 1.1 | Prepared for Project Review

| Item | Details |
| --- | --- |
| Project | University Services Management System (USMS) |
| Team | 6 members |
| Technology | ASP.NET Core Web API, C#, SQL Server, EF Core, ASP.NET Core Identity, HTML/CSS/Bootstrap/JavaScript, Swagger, xUnit, Git/GitHub |
| Requirements baseline | USMS SRS Version 1.1 |
| Purpose | Plan scope, schedule, responsibilities, risks, quality measures, and team communication. |

Scope baseline: Queue / Waiting Management is excluded. Feature 8 is Service Information & Requirements Management.

# 1. Project Proposal

## 1.1 Problem and Proposed Solution

Students may need to visit several offices, ask repeatedly about required documents, follow up manually on requests, and coordinate appointments with limited visibility into progress. USMS proposes a web-based portal where students can browse service requirements, submit and track requests, book eligible appointments, submit complaints, and receive in-app notifications. Employees process assigned work within their departments; Managers monitor permitted operational indicators; Admins manage users, departments, services, and service information.

## 1.2 Objectives

Centralize information about selected university services and their requirements.

Make service requests traceable through clear status changes.

Manage appointment capacity, booking, cancellation, and attendance rules.

Support complaint submission, assignment, and resolution.

Enforce role-based access, student record ownership, and employee department boundaries.

Provide database-backed in-app notifications and a basic dashboard.

## 1.3 Users and Stakeholders

| Role | Main Responsibilities |
| --- | --- |
| Student | Browse services; submit/track own requests; book/cancel eligible appointments; submit/track own complaints; read notifications. |
| Employee | Process requests within assigned department; handle assigned complaints; record appointment attendance where authorized. |
| Manager | Monitor authorized operational indicators and oversee complaint assignment where permitted. |
| Admin | Manage accounts/roles, departments, services, service information, and settings. |
| Supervisor / Team | Supervisor reviews deliverables; team designs, builds, tests, documents, and demonstrates the system. |

## 1.4 Scope and Deliverables

| Included in Scope | Out of Scope |
| --- | --- |
| Authentication and role-based access; department and service management; service information and requirements; service requests; appointment slots and bookings; general complaints; in-app notifications; basic dashboard. | Queue tickets/waiting-time tracking; QR check-in; online payments; official PDF/signatures; SMS/email/push/SignalR; external integrations; AI; transportation; lost-and-found; maps; ratings; native mobile app; advanced analytics. |

Key deliverables: Project Planning & Management; approved SRS v1.1; ERD/database design and relevant UML diagrams; working web/API application; xUnit and manual test evidence; README/setup guide; final report and presentation.

# 2. Project Plan

## 2.1 Planning Assumptions

Six beginner developers, with approximately 2–3 hours per member per day subject to university workload.

SRS v1.1 is the scope baseline; additions require team review and supervisor approval when required.

Course checkpoints currently understood: System Analysis & Design by 6 November, code/implementation by 30 November, and final presentation/testing by 4 December 2026. Confirm these dates with the supervisor.

Member names are assigned below; workload can be adjusted after the first progress review.

## 2.2 Schedule and Milestones

| Period | Main Work | Milestone / Evidence |
| --- | --- | --- |
| 19–23 Oct | Confirm scope, responsibilities, backlog, risks, KPIs, Git workflow. | Planning baseline and task board reviewed. |
| 24–30 Oct | Finalize requirements, user stories/use cases, initial ERD and data dictionary. | Requirements and initial design reviewed. |
| 31 Oct–6 Nov | Finalize ERD, schema, architecture, API boundaries and UML. | System Analysis & Design package ready by 6 Nov. |
| 7–13 Nov | Set up solution, Identity, database/migrations, departments/services, shared API conventions. | Runnable foundation and first endpoints. |
| 14–20 Nov | Build requests, service information, appointments, complaints, notifications, and UI integration. | Core modules integrated. |
| 21–25 Nov | Complete authorization, validation, dashboard, business rules, end-to-end workflows. | Main user journeys working. |
| 26–30 Nov | xUnit/manual tests, fixes, seed data, README, clean-clone verification. | Runnable implementation ready by 30 Nov. |
| 1–4 Dec | Regression testing, demo data, slides, rehearsal and final documentation. | Final presentation and evidence by 4 Dec. |

## 2.3 Work Breakdown

| Work Package | Activities / Evidence |
| --- | --- |
| Management | Backlog, weekly planning, meeting notes, risk/issue log, change control. |
| Requirements & Design | SRS, user stories/use cases, ERD, schema, architecture and UML. |
| Foundation & Security | Project setup, Identity, roles, authorization, validation, API conventions. |
| Business Features | Departments, services, service information, requests, appointments, complaints, notifications. |
| UI & Integration | Responsive pages, API integration, role-aware navigation, end-to-end workflows. |
| Quality & Release | xUnit/manual tests, defect fixes, seed data, README, final demo. |

# 3. Team Members and Responsibilities

| Member | Primary Ownership | Key Tasks |
| --- | --- | --- |
| Mohammed Osama Mofadal | Coordinator & Security | Track milestones/backlog; coordinate merges; configure solution; implement Identity, roles, account status and authorization policies. |
| Ahmed Yasser Mohamed | Departments & Services | Department CRUD; employee-department assignment; service CRUD, active status, department assignment, appointment-support settings. |
| Maqar Ashraf Murid | Service Requests | Request creation/listing; request types and validation; status transitions; cancellation before review; rejection reason; department permissions. |
| Mayar Yasser Abbas | Appointments | Appointment slots, availability, capacity validation, booking/cancellation rules, duplicate-submission protection, attendance and NoShow. |
| Basmala Mossad Sayed | Service Information & Student UI | Service descriptions, eligibility conditions, required documents, instructions, optional processing duration; student service catalog and UI integration. |
| Esraa Mahmoud Mohamed | Complaints, Notifications & Dashboard | Complaint workflow and assignment; in-app notifications/read state; basic dashboard counts; support test summary. |

Shared rule: each member tests and documents their own module. All members review integration, use feature branches/pull requests, keep the shared branch runnable, and help resolve blockers. These assignments are proposed and may be adjusted by team agreement.

# 4. Risk Management

| Risk | Level | Mitigation | Owner |
| --- | --- | --- | --- |
| Beginner team underestimates effort | High | Build a minimal end-to-end workflow early; split tasks small; review progress weekly; prioritize core requirements. | All / Mohammed |
| Modules do not integrate | High | Agree on entity names, routes, DTOs, status values and branch rules early; integrate every week. | Mohammed |
| Scope creep delays delivery | High | Use SRS v1.1 as baseline; review effort and schedule impact before accepting changes. | All |
| Unauthorized data access | High | Enforce backend permissions; test student ownership, employee department scope, Manager and Admin permissions. | Mohammed / Maqar / Esraa |
| Appointment capacity/duplicate booking defects | High | Validate on server; test full slots, repeated requests, cancellations, date/time boundaries and concurrency where feasible. | Mayar |
| Late bugs or setup failures | Medium/High | Test during development; keep a defect log; use migrations/seed data; verify setup from a clean clone. | All / Esraa |
| University workload reduces availability | Medium/High | Keep tasks small, report blockers early, identify backup help, and replan without expanding scope. | All |

Review risks weekly. Each risk should have an owner and action. If a milestone is at risk, reduce optional polish or redistribute tasks rather than silently dropping required features.

# 5. Key Performance Indicators (KPIs)

| KPI | Target / How to Measure |
| --- | --- |
| Milestone progress | Complete planned milestones on time or record an agreed replan; review task board weekly. |
| Requirements coverage | Every must-have SRS requirement mapped to implementation or a documented open issue/test. |
| Core workflow quality | Acceptance tests pass for access control, requests, appointments, complaints, and notifications. |
| Security | No unresolved critical/high-severity authorization defects before release. |
| Appointment rules | Tests pass for capacity, cancellation cutoff, past dates, and duplicate booking attempts. |
| Automated tests | All committed xUnit tests pass on the release candidate. |
| Reproducibility | A teammate can run the system from a clean clone using the README, migrations, and sample data. |
| Documentation | SRS, setup guide, test summary, task allocation, and presentation reviewed before submission. |

These are proposed targets, not claims of achieved results. Record actual pass/fail results during testing.

# 6. Communication and Change Control

| Activity | Frequency / Rule |
| --- | --- |
| Team progress | At least twice weekly: each member reports Done / Next / Blocked. |
| Planning and review | Weekly review of tasks, risks, blockers, milestone status and next priorities. |
| Integration | At least weekly and before every milestone; review pull requests and run the application. |
| Supervisor checkpoint | Present required evidence, confirm expectations, and record feedback/actions. |
| Change control | Document reason, benefit, effort, dependencies, testing and schedule impact; obtain approval when required; update SRS, task board and design together. |

## 6.1 Definition of Done

Acceptance criteria met and input/error cases handled.

Backend authorization and ownership/department rules verified.

Relevant xUnit or documented manual tests pass.

Feature integrated without breaking existing workflows.

Necessary setup or user notes updated.

# 7. Constraints and Approval

Technology baseline: ASP.NET Core Web API, C#, SQL Server, EF Core, ASP.NET Core Identity, HTML/CSS/Bootstrap/JavaScript, Swagger, xUnit and Git/GitHub.

Use synthetic/sample data for development and demonstrations; do not use real student personal data.

Deployment may be local or in a supervisor-approved environment unless a hosting requirement is specified.

Queue / Waiting Management remains excluded unless formally approved as a scope change.

| Review Role | Name / Signature | Date / Comments |
| --- | --- | --- |
| Project Coordinator | Mohammed Osama Mofadal | ________________________ |
| Team Representative | ________________________ | ________________________ |
| Project Supervisor | ________________________ | ________________________ |